## WBS
WBS-L1-ID | Level-1 WBS | WBS-L2-ID | Level-2 WBS | WBS-L3-ID | Level-3 WBS | Estimted Time | Start Date | End Date | Complete [%]
1 | WEB-FORM | 1.1 | Form Structure consist all the fields | 1.1.1 | Date - Calender will show to select the date Floor - Text Box List of equipment - Dropdown and multiple selcetion should be allowed Smoking restrictions - Tick and Untick feature impliment for this. | 2d | 18-02-2023 | 19-02-23 | 50%
|  |  |  | 1.1.2 | List should show as per the searched criteria below. | 1d | 20-02-23 | 20-02-23 | 80%
|  |  |  | 1.1.3 | Include the pagination at below of the page. | 1d | 21-02-23 | 21-02-23 | 100%
2 | Addons in WEB FORM | 2.1 | User registration | 2.1.1 | Designing of the registeration page. | 1d | 21-02-23 | 21-02-23 | 100%
| Addons in WEB FORM |  |  | 2.1.2 | Include the following fields - Name Email Mobile No. Password Confirm Password Google Captcha Submit Button | 1d | 20-02-23 | 20-02-23 | 100%
|  |  |  | 2.1.3 | OTP Verification page design | 2d | 24-02-23 | 25-02-23 | 30%
[5 empty] | OTP Page consist the following - Email ID and other details. OTP Entering Box Submit Button | 5h | 19-02-23 | 24-02-23 | 40%
|  |  |  | 2.1.4 | OTP Success verification Page | 2d | 25-02-23 | 26-02-23 | 90%
|  | 2.2 | Booking of the office place | 2.2.1 | Booking office Page designning | 1d | 20-02-23 | 20-02-23 | 60%
|  |  |  | 2.2.2 | The following fields should be there - Office location - Dropdown[Single selection] Date from which to which need the booking. Submit button | 2d | 18-02-2023 | 19-02-23 | 0%
|  | 2.3 | User roles | 2.3.1 | User types are - 1. Normal User 2. Manager | 4h | 20-02-23 | 20-02-23 | 20%
|  |  |  | 2.3.2 | Normal User specific page designning. | 4h | 19-02-23 | 19-02-23 | 0%
|  |  |  | 2.3.3 | Manager user specific page designing | 4h | 20-02-23 | 20-02-23 | 0%
|  |  |  | 2.3.4 | DB setup for both users. | 5d | 23-02-23 | 23-02-23 | 0%
|  |  |  | 2.3.5 | Mapping users with their respective work area. | 4d | 24-02-23 | 24-02-23 | 0%
|  | 2.4 | Native Mobile Application | 2.4.1 | Splash Screen | 4h | 24-02-23 | 24-02-23 | 0%
|  |  |  | 2.4.2 | Sign and Signup page creation and setup | 5d | 26-02-23 | 2023-02-03 | 0%
|  |  |  | 2.4.3 | Booking office screen designing and setup | 3d | 28-02-23 | 2023-02-03 | 0%
|  |  |  | 2.4.4 | Web- form screen | 2d | 28-02-23 | 2023-02-03 | 0%
|  |  |  | 2.4.5 | Web- form DB Connection | 3d | 2023-03-03 | 2023-03-03 | 0%